## projects
Sample Portfolio Project List
Project # | Priority | project Name | Project Description | Parent Project | Precursor | Hours SDE | Max SDE Assigned | Hours SDET | Hours Manual Test | Hours Solution Architect | Hours Scum Master | Hours PM | Hours IA | Hours Prod Mgmt | Hours GUI Design | Bare Metal Hardware | VM Hardware | Software Purch | Cloud Hosting | Maint | Target Date | Sponsors | Project MGR | Needed By Projects | Project Approved for Work | NPV Business Value | Portion Complete | Min Duration days | Min Completion in Days | Max Completion in days | Must Start Date | Must Stop Date
W001 | 12 | Update Product Search Engine |  | P003 |  | 1500 | 4 | 300 | 20 | 288 | 212.8 | 106.4 | 20 | 127.68 | [7 empty] | rio | dodge | W002 | Y | 150000 | 0 |  |  | 50
W002 | 14 | Update product search UI | Re-write product search UI for RIA following new style guide and support predictive search as they type and auto complete. | P003 | W001 W006 | 460 |  | 92 | 300 | 88.32 | 102.532 | 51.266 | 85 | 61.5192 | [7 empty] | versa | nisan |  | Y | 120000 |  |  |  | 90
P003 | 16 | Update Search Experience | Program to update search experience |  |  | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | [5 empty] | 2019-12-31 | Weinstien | Romero |  | Y | 130000
W006 | 19 | Data feed for product search engine | Detect changes in product catalog and feed to new product search engines Via Queue | P003 |  | 460 |  | 92 | 10 | 88.32 | 67.032 | 33.516 | 20 | 40.2192 | [7 empty] | expedition |  | W002 W001 | Y | 1400000
W005 | 21 | SSO for all web applications | Upgrade shopping, product search, vendor search and product support with SSO |  | W004 | 2400 |  | 480 | 500 | 460.8 | 384.08 | 192.04 | 0 | 230.448 |  | 110000 |  | 25000 | 15000 |  |  | Epstien | Ford |  | Y | [7 empty] | Initial SSO must fund al hardware / software through end of first year when implemented.
W013 | 24 | GDPR Compliance Site Guide & Refernce Imp |  | P004 |  | 200 |  | 40 | 0 | 78.4 | 32.04 | 16.02 | 2 | 2 | 250 | [6 empty] | gov | edsel |  | Y
W011 | 27 | GDPR compliance product search |  | P004 | W013 | 100 |  | 20 | 100 | 19.2 | 24.12 | 12.06 | 2 | 14.472 | [7 empty] | gov | edsel |  | Y | 800000
W012 | 30 | GDPR compliance product support site |  | P004 | W013 | 100 |  | 20 | 100 | 19.2 | 24.12 | 12.06 | 2 | 14.472 | [7 empty] | gov | edsel |  | Y | 500000
W004 | 33 | SSO Infrastructure & RI | Install SSO servers and provide reference implementation for all developers. | P003 |  | 250 |  | 50 | 20 | 56 | 39.6 | 19.8 | 20 | 23.76 | 50 | [6 empty] | escape |  |  | Y | 250000
W008 | 37 | GDPR compliance Shopping Site | Update main shopping site for GDPR compliance | P004 | W013 | 100 |  | 20 | 100 | 19.2 | 24.12 | 12.06 | 2 | [8 empty] | gov | edsel |  | Y | 130000
P004 | 41 | GDPR compliance | Program for overall GDPR compliance |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [5 empty] | 2019-09-30 | gov | edsel |  | Y | 1500000
KTLO | 1 | Keep the Lights on | Maintenance & Support |  |  | 1200 | NA | 240 | 0 | 230.4 | 167.04 | 83.52 | 0 | 100.224 | 0 | [6 empty] | CIO | pinto |  | Y | 2500000 |  | 264
W017 | 21.001 | SSO Infrastructure KTLO | Maintain & Run SSO Infrastrastruct |  | W005 | 200 | NA | 40 | 100 | 38.4 | 37.84 | 18.92 | 0 | 22.704 | 0 | 12000 |  |  | 35000 | 5000 | 2019-12-31 | CIO | [5 empty] | 264 |  |  | 2020-01-01 |  | This project continues maintenance and operations into next year
Note on H3: joexdobs: Only fill in the Max assigned when you want to override what is specified as default in the resource spreadsheet
Note on AC3: joexdobs: Use Minimum Duration to force a project to span at least this many days. This can be useful for support or projects that need some progress but which must be prevented from consuming too many resourced too fast. Some maintenance activities are like this. For keep the lights on activities that need to be tracked like a project but span time it is better to specify a must start date and a target date which will override the priority if needed. This setting is generally better for those that can be moved on roadmap based on priroity but should still meter actiity to fit the specired duration.
Note on AD3: joexdobs: min Completion Days to augment min Duration Days. Min Completion is relative to start of planning while min duration is relative to start of the project. When we know that we want to end a project exactly 365 days from the start of planning then it is easier to use min completion and still let start time vary. If you set min duration and min completion to the same value then you can gaurante a start and end time relative to project start.
Note on AE3: joexdobs: Some reports will be modified to show in warning color when project completion is after the specified number of days from the start of planning. The system can also use max duration to optimize or recomend changes that can reduce max duration. Can be specified directly but is normally set from from the planning start date and target date. Normally set from target date but when you do not know when approval to start work or funding will be recieved then it is easier to use this setting rather that continue to recompute target dates as funding approval for the entire set remains unknown.
Note on AF3: joexdobs: Items with a Must Start Date will be started on that date regaurdless of priority. They will start on that date until complete. If they have a mustStartDate and a target Date then they will run for that length of time and will only consume resources at a rate that will meet those goals. Those that have must start date and a target date will ignore duration. Those with must start date and a duration will will compute a end date.
Note on AC15: joexdobs: Used 22 working days per month times 12 months
Note on V16: joexdobs: Items that have minimum duration and a target date will be stretched to reach the target date or the duraction whichever is shorter.